## User Stories
ID | Story Title | Points | Priority | As a/an [user] | I want [functionality] | So that [value] | User Story | NFR | Definition of Done / Blockers | Epic ID | Status | Notes
M1 | Team Creation | 3 | High | Manager | to create a team | so my players can join | As a/an Manager, I want to create a team, so that so my players can join |  | Managers can successfully create a team |  | Open
T2 | Team Signup | 3 | High | Teen | to join a team | I can play | As a/an Teen, I want to join a team, so that I can play |  | A teen can register to play in the tournament |  | Open
G3 | Team Signup Permission | 1 | High | Guardian | join a team on behalf of my child | they can play | As a/an Guardian, I want join a team on behalf of my child, so that they can play |  | A parent can register their kid to play in the tournament |  | Open | This story is similar to T2, which is why it's only 1 point
U4 | Team chat | 13 | Low | User | chat with my teammates | we can coordinate and chat | As a/an User, I want chat with my teammates, so that we can coordinate and chat |  | Chats can be sent between one user (player, parent, coaches) to another |  | Open
V5 | Game Schedule | 2 | High | Visitor | see the game schedule | i can know when the games are | As a/an Visitor, I want see the game schedule, so that i can know when the games are |  | Any user can see the game schedule for all teams |  | Open
V6 | Live Feed | 3 | Low | Visitor | See the Game Live on the website | I can watch the game live | As a/an Visitor, I want See the Game Live on the website, so that I can watch the game live |  | Any user can see the Game Live, and can watch the livestream |  | Open
V7 | Check Game Stats | 2 | Medium | Visitor | to see stats of games | i can know the results | As a/an Visitor, I want to see stats of games, so that i can know the results |  | Any user can see the game stats during or after the game |  | Open
V8 | Check Player Stats | 2 | Low | Visitor | to see stats of a player | I can see how a player has performed | As a/an Visitor, I want to see stats of a player, so that I can see how a player has performed |  | Any user can see the stats of each individual player for every game they played |  | Open
A9 | Scheduling Algorithm | 3 | High | Admin | to create the schedule for all 30 teams | each team knows who and when they are going to play | As a/an Admin, I want to create the schedule for all 30 teams, so that each team knows who and when they are going to play |  | An admin can create all teams and know when they are going to play |  | Open
M10 | Manager Control | 8 | High | Manager | add, remove, update, teammates | i can manage my team | As a/an Manager, I want add, remove, update, teammates, so that i can manage my team |  | When User's with Manger status can manage their team |  | Open
A11 | Multiple Tournaments | 2 | High | Admin | to create multiple tournaments | we can create tournaments with different age groups | As a/an Admin, I want to create multiple tournaments, so that we can create tournaments with different age groups |  | When an admin can create tournaments easily |  | Open
U12 | Set Pictures | 2 | Medium | Manager | set roster pictures of parents and players | users can see who is on what team | As a/an Manager, I want set roster pictures of parents and players, so that users can see who is on what team |  | User only can see the photos of the managers and players |  | Open
A13 | Set Theme | 1 | low | Admin | to set the colors of the website theme | i can change them as needed | As a/an Admin, I want to set the colors of the website theme, so that i can change them as needed |  | The theme is displayed correctly on the website |  | Open
A14 | Set Sponsor Logos | 2 | Medium | Admin | add and edit sponsor logos | sponsors can be advertised | As a/an Admin, I want add and edit sponsor logos, so that sponsors can be advertised |  | The admin can add and edit sponsor logos |  | Open
V15 | View Competition Rules | 1 | Medium | Visitor | view the specific rules of this competition | i can know the competition rules | As a/an Visitor, I want view the specific rules of this competition, so that i can know the competition rules |  | The rules of the competition can be viewed on the website |  | Open
A16 | Set Competition Rules | 1 | Medium | Admin | set the specific rules | i can formalize the contest | As a/an Admin, I want set the specific rules, so that i can formalize the contest |  | The rules of the tournament can be uploaded and displayed |  | Open
T17 | Teen Account Creation | 2 | High | Teen | to make a teen account | i can join teams | As a/an Teen, I want to make a teen account, so that i can join teams |  | Teens can create an account and join teams |  | Open
G18 | Guardian Account Creation | 1 | High | Guardian | to make a guardian account | i can optinally create a team or view my kid's team | As a/an Guardian, I want to make a guardian account, so that i can optinally create a team or view my kid's team |  | Be able to create an guardian account that is capable to manage a team |  | Open | This story is similar to T17, which is why it's only 1 point

## M’s guesses
S0
M1 | 3
T2 | 3
G3 | 3
U4 | 11
V5 | 2
V6 | 13
V7 | 3
V8 | 3
A9 | 5
A10 | 2
M11 | 11
A12 | 1
U13 | 3
A14 | 3
A15 | 1
A16 | 1
V17 | 1
A18 | 2
T19 | 8
G20 | 8

## Tasks
ID | Task Title | Task Description | Story ID

## Epics
ID | Epic Title | Description

## NFR
ID | Title | Category | Description | Affects
1 | Color Scheme | Visual / Design | The color scheme for the app should be *** | All
2 | Understand a NFR | Understandability | Simple example for the students to understand | Some